## Feedbackissues
Platform | status | version (when done) | blocker | Entry point/Screen/Flow | Feedback/issues | Type | Description (put screenshot/vid on this link | Reported by | Ticket | Link to Gdrive of screenshot/ video | Remarks
Android | not bug |  |  | Spend | Spend tracker not under paywall (should be Ultra/Premium) | functionality | Spend tracker not under paywall | Niv
iOS | not bug |  |  | Spend tracker | Spend tracker not under paywall | functionality |  | Nalim
Android |  |  | yes | Paywall | Direct Debit information popup showing when clicked on "see all benefits" | functionality | Direct Debit information popup showing when clicked on "see all benefits" | Niv
Android |  |  | yes | From Entry point brain | Latency, takes 3-4 sec to load the summary screen | functionality | Latency, takes 3-4 sec to load the summary screen | Niv
Android | not bug |  |  | Paywall | On Upsell screen validity shows 2 months, while it is told 30 days | functionality | validity shows 2 months, while it is told 30 days | Niv
Android | done | BE | yes | Paywall | FTW is not the copy for 52-week challenge, customer will not know this | design | FTW is not the copy for 52-week challenge, customer will not know this | Niv
iOS | done | BE | yes | 52-week challenge/ Brain | FTW is not the copy for 52-week challenge, customer will not know this | design | https://drive.google.com/file/d/1qcnp8pyiFEkglSp2pFtny8pjNhvnTGoH/view?usp=sharing | Nalim
iOS |  |  | yes | Paywall | Very small tappable area (Close x cta not working on upsell screen) | functionality |  | Efi
iOS |  |  | yes | Brain configuration upsell | am i supposed to see the summary screen instead of landing directly at the expanded view? | functionality | 1. Why rounds up is triggering upsell if its a free feature? 2. Are we showing contextual upsell screen if user clicked Pay day or any other rules which has been put behind a paid plan The expectation is we open contextual upsell screen if feature is paid and user is clicking that feature (e.g. brain free feature should not open upsell screen but paid should open contextual summary upsell screen .) In case of automation rule or a feature requiring bank linking , bank linking flow supersedes upsell and is priortised | Sia
iOS |  |  | yes | Brain configuration upsell |  | functionality |  | Sia
Both | not bug |  |  | General upsell | On android Premium plan can't be seen clearly when selected on initial upsell | design |  | Elise |  | See Premium it is faded - doesn't look like I selected it
Android |  |  | yes | General upsell | Premium tab copy is broken in two lines | design | https://drive.google.com/file/d/1mOQ2mTVSG8IFgRhsF39sihq5a247FWZp/view?usp=sharing | Nalim
Android |  |  |  | General upsell | Direct Debit is hard to click | functionality |  | Nalim
Android |  |  | yes | Paywall | Summary and expanded screen Ultra is using Premium colour, and Premium is using Ultra colour | design | https://drive.google.com/file/d/1VodAXIzltKeANn0QiotatOGLdb9t4rtk/view?usp=sharing https://drive.google.com/file/d/1_6j-LC7WlqS-rYXKjgfp5tkIo9KHAgj6/view?usp=sharing | Nalim
Android |  |  | yes | Create pocket | Old Splash screen appearing before summary screen | Both | https://drive.google.com/file/d/1-xe6PiDKOtkq-y0OgE9YHYvWn7tY_Kaw/view?usp=sharing | Nalim
Both |  |  | yes | General summary Screen | Button copy is wrong. Change button copy to "See all benefits" | design | https://drive.google.com/file/d/1X1QYqJlxZ1iF6KrS4Hr7J6cmg6jJjbBU/view?usp=sharing | Nalim
iOS |  |  | yes | General expanded screen | Basic does not appearing on Non-contextual upsell. Plans ordination is the opposite as it should be (Premium first) | functionality | https://drive.google.com/file/d/1fhTMhhwW_Yp0KdcSx8j6GAKhC0X8jY5b/view?usp=sharing | Nalim
iOS |  |  | yes | General summary Screen | Summary screen cards are not sticking to the middle during the scroll. | design | https://drive.google.com/file/d/1LYbWF6GbtiE7fn5B6xiSW6Hy-vGu6vDC/view?usp=sharing | Nalim
iOS |  |  | yes | General summary Screen | The pagination icon is not working. The distance between card and pagination should be 16px. | design | https://drive.google.com/file/d/1LYbWF6GbtiE7fn5B6xiSW6Hy-vGu6vDC/view?usp=sharing | Nalim
iOS |  |  | yes | General Summary Screen | Cards have size variations in the same visualisation. | design | https://drive.google.com/file/d/1LYbWF6GbtiE7fn5B6xiSW6Hy-vGu6vDC/view?usp=sharing | Nalim
iOS |  |  | yes | Recurring Orders/ Investing | Old designs appearing on Recurring Orders entry point | functionality | https://drive.google.com/file/d/1Asx5Naw0s6O_SMl5aJmwMhMcoDczTSO6/view?usp=sharing | Nalim
iOS |  |  | yes | General | When I click in "See all benefits" it send me t o the wrong expanded screen | functionality | https://drive.google.com/file/d/19_GGzO78bpWXJ7bQ3iYQQLNTs3tCkTIY/view?usp=sharing | Nalim
Android |  |  |  | General expanded screen | Improve distances on plans page header | design |  | Nalim
iOS |  |  |  | General Summary Screen | Pagination appearing in single card page | design | https://drive.google.com/file/d/1Ph-qKjWQ9F_Kv93y7gIqj4rOYzn6uiyI/view?usp=sharing | Nalim
iOS |  |  |  | Brain configuration upsell | we usually spell direct debit with capital letters Direct Debit, the link is tiny and challenging to tap on it but not a huge issue | design |  | Sia
Android |  |  |  | Paywall | Copy should be "The 1p challenge +..." | design | https://drive.google.com/file/d/1H_QuuqPJZh4we1y551VoLr2WPrF_YEMr/view?usp=sharing | Nalim
iOS |  |  |  | 1p Challenge/ Brain | 1P Challenge copy is wrong | design | https://drive.google.com/file/d/1qcnp8pyiFEkglSp2pFtny8pjNhvnTGoH/view?usp=sharing | Nalim
Android | done |  |  | Paywall | Padding bvetween header "Pick your plan" and plan switching tab is too much. Same too much space between sections like saving and investing in expanded upseel screen | design |  |  | https://withplum.atlassian.net/browse/CORX-3508
iOS |  |  |  | Paywall | Padding bvetween header "Pick your plan" and plan switching tab is too much. Same too much space between sections like saving and investing in expanded upseel screen | design
iOS |  |  |  | general | Adjust paddings above "For savings" and above subs badge row | design | https://drive.google.com/file/d/1k8Pcx5uqvKZswJjCZkkOHdc_GMw2v4DU/view?usp=sharing | Nalim

## Android
Entry Point | Android Tickets | completion date (ETA) | Code Owner (current) | Status | Action | Android E2E Created | iOS E2E Created | Module | Squad Ownership (Q4 2024) | Difficulty | SubscriptionUpsellSource |  |  | Squad |  | Owner
Manage Subscription Fragment | https://withplum.atlassian.net/browse/CORX-2846 | Done | Subscriptions | DONE | Show V1 all plans | Yes | No | Subscriptions | Activation | Very Low | CHANGE_PLAN |  |  | NA | OWBL | Sia, Allan
Your Account Fragment | https://withplum.atlassian.net/browse/CORX-2856 | Done | Subscriptions | DONE | Show V1 all plans | Yes | No | Subscriptions | Payments | Very Low | UPGRADE_ME |  |  | NA | OWBL | Athina, carlos
Brain Fragment | https://withplum.atlassian.net/browse/CORX-2857 | Done | Subscriptions | DONE | Navigate to Upsell using Upsell Source | Yes | No | Brain | Payments | Low | STOCKS_RECURRING_ORDER
Navigation Resolver Fragment | https://withplum.atlassian.net/browse/SPEND-2478 | Tue 14th Jan | Spend | DONE | Navigate to Upsell for Card upsell | Yes | No | Card | Payments | Very Low | CARD_TILE
Crypto Coin Details Fragment | https://withplum.atlassian.net/browse/CORX-2859 | Done | Trading | DONE | Navigate to Price Alerts upsell | Yes | No | Crypto | Trading | Medium | PRICE_ALERTS
Confirm Order Fragment | https://withplum.atlassian.net/browse/CORX-2860 | Done | Trading | DONE | Navigate to ETFS Bracket 1 upsell | Yes | No | Investments | Trading | Medium | ETFS_BRACKET_1
Order Preview Fragment | https://withplum.atlassian.net/browse/CORX-2861 | Done | Trading | DONE | Navigate to ETFS Bracket 1 upsell | Yes | No | Investments | Trading | Medium | ETFS_BRACKET_1 |  |  | NA (F&F) | OWBL | Lia, nelson
Account Type Selection List | https://withplum.atlassian.net/browse/CORX-2862 | Tue 14th Jan | Payments | DONE | Navigate to Interest Upsell | Yes | No | Pockets | Spend | Very Low | INTEREST
Create Pocket Fragment | https://withplum.atlassian.net/browse/CORX-2863 | Tue 14th Jan | Payments | DONE | Navigate to Pockets Customisation upsell. | Yes | No | Pockets | Spend | Low | POCKET_CUSTOMIZATION
Delete Account Confirmation Fragment | https://withplum.atlassian.net/browse/CORX-2864 | Tue 14th Jan | Payments | DONE | Navigate to Unlimited Pockets upsell. | Won't Do | No | Pockets | Spend | Low | UNLIMITED_POCKETS
CashIsaPocketFragment | https://withplum.atlassian.net/browse/WM-3673 | TBD ~20th | Wealth Management | DONE | Navigate to three possible upsell types | Yes | Yes | Pockets | Wealth Management | Low | CASH_ISA_ONBOARDING | CISA_POCKET_CTA_GEN | CASH_ISA_POCKET |  |  | Emrah, Ishaan
Save Fragment | https://withplum.atlassian.net/browse/CORX-2866 | Tue 14th Jan | Payments | DONE | Navigate to Unlimited Pockets upsell | Yes | No | Pockets | Spend | Low | UNLIMITED_POCKETS
Brain Configuration Fragment | https://withplum.atlassian.net/browse/CORX-2867 | Tue 14th Jan | Activation | DONE | Navigate to Post Onboarding upsell | Won't do | No | PostOnboarding | Activation | Medium | POST_ON_BOARDING |  |  |  |  | Sia, Allan
Combo Saver Fragment | https://withplum.atlassian.net/browse/SPEND-2478 | Tue 14th Jan | Spend | DONE | Navigate to Upsell for each combo saver type | Won't Do | No | Savers | Spend | Low | FTW_WEEK_CHALLENGE, RAINY_DAY, NAUGHTY_RULE, ONE_PENNY_CHALLENGE
Saver Navigation Resolver Fragment | https://withplum.atlassian.net/browse/SPEND-2478 | Done | Spend | DONE | Navigate to Upsell | Yes | No | Savers | Spend | Low | FTW_WEEK_CHALLENGE, RAINY_DAY, NAUGHTY_RULE, ONE_PENNY_CHALLENGE
Spend Fragment | https://withplum.atlassian.net/browse/SPEND-2478 | Tue 14th Jan | Spend | DONE | Navigate to Generic upsell | Yes | No | Spend | Spend | Low | UPGRADE_ME
Spend Fragment | - | Tue 14th Jan | Spend | DONE | Navigate to Naughty Rule upsell | Yes | No | Spend | Trading | Low | NAUGHTY_RULE |  |  | Avail |  | Elise, Stelios
Spend Tracker Fragment | - | Tue 14th Jan | Spend | DONE | Navigate to Spend Tracker upsell | Yes | No | Spend | Trading | Low | SPEND_TRACKER
Home Toolbar Action | https://withplum.atlassian.net/browse/CORX-2872 | Done | Subscriptions | DONE | Upgrade me tap show generic upsell | Yes | No | Widget | Trading | Very Low | UPGRADE_ME
Stock Instrument Fragment | https://withplum.atlassian.net/browse/CORX-2873 | Done | Trading | DONE | Navigate to Price Alerts upsell | Yes | No | Investments | Trading | High | PRICE_ALERTS
Buy Stocks Order Fragment | https://withplum.atlassian.net/browse/CORX-2878 | Done | Trading | DONE | Navigate to recurring orders upsell | Yes | No | Investments | Trading | Medium | STOCKS_RECURRING_ORDER
Fund Instrument Fragment | https://withplum.atlassian.net/browse/CORX-2891 | Done | Trading | DONE | Navigate to upsell then return to feature | Yes | No | Investments | Trading | Medium | FUNDS_BRACKET_1 | ETFS_BRACKET_1 | ETFS_BRACKET_2
Interest Upsell Fragment | https://withplum.atlassian.net/browse/WM-3683 |  | Wealth Management | DONE | Navigate to Interest Upsell, can return to feature | Yes | No | Pockets | Wealth Management | Medium | INTEREST |  |  |  |  | Ishaan, Emrah
Plum Interest MMF Upsell Fragment | https://withplum.atlassian.net/browse/WM-3695 |  | Wealth Management | DONE | Navigate to Generic upsell, can return to feature | Yes | Yes | Pockets |  | Medium | MMF_RECURRING_ORDER, MMF_ONBOARDING
Trading | https://withplum.atlassian.net/browse/TRAD-2618 |  | Trading | DONE |  | Yes | No
Savings (WM) | https://withplum.atlassian.net/browse/WM-3673 |  | Wealth Management | DONE |  | Yes | No
Payments | https://withplum.atlassian.net/browse/PAY-2269 |  | Payments | DONE |  | In Review | No
Epic | https://withplum.atlassian.net/browse/CORX-2845

## iOS
Entry Point | iOS Tickets | completion date (ETA) | Code Owner (current) | Status | iOS E2E Created | Action | Module | Squad Ownership (Q4 2024) | Difficulty | SubscriptionUpsellSource |  |  | Squad |  | Owner
[iOS] App Icon | CORX-3349 |  | Subscriptions | DONE | CORX-3389
[iOS] User Profile Subscription Management | CORX-3350 |  | Subscriptions | DONE | CORX-3390
[iOS] Change Plans | CORX-3391 |  | Subscriptions | DONE | CORX-3390
[iOS] Home Screen CTA | CORX-3351 |  | Subscriptions | DONE | CORX-3390
[iOS] Brain Widget | CORX-3352 |  | Subscriptions | DONE | Can't be done
[iOS] Brain Savers | CORX-3353 |  | Subscriptions | DONE | CORX-3392
[iOS] Brain Recurring | CORX-3354 |  | Subscriptions | DONE | CORX-3398
[iOS] DL "/subscription" | CORX-3355 |  | Subscriptions | DONE | CORX-3399
[iOS] DL "/subscription-checklist" | * To be discussed |  | Subscriptions | NOT STARTED | no
[iOS] DL "/manage_subscription" | * To be discussed |  | Subscriptions | NOT STARTED | no
[iOS] DL "/brain/ftw" | * To be discussed |  | Subscriptions | NOT STARTED | no
[iOS] DL "/brain/rainy-day" | * To be discussed |  | Subscriptions | NOT STARTED | no
Manage Subscription Fragment |  |  | Subscriptions | NOT STARTED | no | Show V1 all plans | Subscriptions | Activation | Very Low | CHANGE_PLAN |  |  | NA | OWBL | Sia, allen
Your Account Fragment |  |  | Subscriptions | NOT STARTED | no | Show V1 all plans | Subscriptions | Payments | Very Low | UPGRADE_ME |  |  | NA | OWBL | Athina, carlos
Brain Fragment |  |  | Subscriptions | NOT STARTED | no | Navigate to Upsell using Upsell Source | Brain | Payments | Low | STOCKS_RECURRING_ORDER
Navigation Resolver Fragment | https://withplum.atlassian.net/browse/SPEND-2478 | Tue 14th Jan | Spend | IN REVIEW | no | Navigate to Upsell for Card upsell | Card | Payments | Very Low | CARD_TILE
Crypto Coin Details Fragment | https://withplum.atlassian.net/browse/TRAD-2719 | Fri 10th Jan | Trading | IN REVIEW | no | Navigate to Price Alerts upsell | Crypto | Trading | Medium | PRICE_ALERTS
Confirm Order Fragment | - | Fri 10th Jan | Trading | IN REVIEW | no | Navigate to ETFS Bracket 1 upsell | Investments | Trading | Medium | ETFS_BRACKET_1
Order Preview Fragment | - | Fri 10th Jan | Trading | IN REVIEW | no | Navigate to ETFS Bracket 1 upsell | Investments | Trading | Medium | ETFS_BRACKET_1 |  |  | NA (F&F) | OWBL | Lia, nelson
Account Type Selection List | https://withplum.atlassian.net/browse/PAY-2269 | Tue 14th Jan | Payments | DONE | no | Navigate to Interest Upsell | Pockets | Spend | Very Low | INTEREST
Create Pocket Fragment | - | Tue 14th Jan | Payments | IN REVIEW | no | Navigate to Pockets Customisation upsell. | Pockets | Spend | Low | POCKET_CUSTOMIZATION
Delete Account Confirmation Fragment |  | Tue 14th Jan | Payments | DONE | no | Navigate to Unlimited Pockets upsell. | Pockets | Spend | Low | UNLIMITED_POCKETS
CashIsaPocketFragment | https://withplum.atlassian.net/browse/WM-3673 |  | Wealth Management | DONE | YES | Navigate to three possible upsell types | Pockets | Wealth Management | Low | CASH_ISA_ONBOARDING | CISA_POCKET_CTA_GEN | CASH_ISA_POCKET |  |  | Emrah, Ishaan
Save Fragment | https://withplum.atlassian.net/browse/PAY-2276 | Tue 14th Jan | Payments | IN REVIEW | no | Navigate to Unlimited Pockets upsell | Pockets | Spend | Low | UNLIMITED_POCKETS
Brain Configuration Fragment | https://withplum.atlassian.net/browse/AC-2313 | (pending subs component completion) | Activation | DONE | no | Navigate to Post Onboarding upsell | PostOnboarding | Activation | Medium | POST_ON_BOARDING
Combo Saver Fragment | - | Tue 14th Jan | Spend | IN REVIEW | no | Navigate to Upsell for each combo saver type | Savers | Spend | Low | FTW_WEEK_CHALLENGE, RAINY_DAY, NAUGHTY_RULE, ONE_PENNY_CHALLENGE
Saver Navigation Resolver Fragment | - | Tue 14th Jan | Spend | IN REVIEW | no | Navigate to Upsell | Savers | Spend | Low | FTW_WEEK_CHALLENGE, RAINY_DAY, NAUGHTY_RULE, ONE_PENNY_CHALLENGE
Spend Fragment | - | Tue 14th Jan | Spend | IN REVIEW | no | Navigate to Generic upsell | Spend | Spend | Low | UPGRADE_ME
Spend Fragment | - | Tue 14th Jan | Spend | IN REVIEW | no | Navigate to Naughty Rule upsell | Spend | Trading | Low | NAUGHTY_RULE |  |  | Avail |  | Elise, Stelios
Spend Tracker Fragment | - | Tue 14th Jan | Spend | IN REVIEW | no | Navigate to Spend Tracker upsell | Spend | Trading | Low | SPEND_TRACKER
Home Toolbar Action |  |  | Subscriptions | NOT STARTED | no | Upgrade me tap show generic upsell | Widget | Trading | Very Low | UPGRADE_ME
Stock Instrument Fragment | https://withplum.atlassian.net/browse/TRAD-2719 | Fri 10th Jan | Trading | IN REVIEW | no | Navigate to Price Alerts upsell | Investments | Trading | High | PRICE_ALERTS
Buy Stocks Order Fragment | - | Fri 10th Jan | Trading | IN REVIEW | no | Navigate to recurring orders upsell | Investments | Trading | Medium | STOCKS_RECURRING_ORDER
Fund Instrument Fragment | - | Fri 10th Jan | Trading | IN REVIEW | no | Navigate to upsell then return to feature | Investments | Trading | Medium | FUNDS_BRACKET_1 | ETFS_BRACKET_1 | ETFS_BRACKET_2
Interest Upsell Fragment | https://withplum.atlassian.net/browse/WM-3673 |  | Wealth Management | DONE | no | Navigate to Interest Upsell, can return to feature | Pockets | Wealth Management | High | INTEREST |  |  |  |  | Ishaan, Emrah
Plum Interest MMF Upsell Fragment | - |  | Wealth Management | DONE | YES | Navigate to Generic upsell, can return to feature | Pockets |  | Medium | MMF_RECURRING_ORDER, MMF_ONBOARDING

## Sources List
List of Sources | Plans Included | Comment | entry point traffic: https://withplum.cloud.looker.com/dashboards/334?M+Month=6+month+ago+for+6+month
UPGRADE_ME | [PREMIUM, ULTRA, PRO, BASIC] |  | https://withplum.cloud.looker.com/explore/plum/subscription_source_monthly?qid=WAhC43LKVZGH7PScWaaRVT&origin_space=403&toggle=dat,pik,vis
APP_ICON | [PREMIUM, ULTRA, PRO, BASIC] | Doesn't exist on Android
CHANGE_PLAN | [PREMIUM, ULTRA, PRO, BASIC]
SUB_TAB | [PRO, ULTRA, PREMIUM] | iOS only
INTEREST | [PREMIUM, ULTRA, PRO, BASIC]
POST_ONBOARDING | [PREMIUM, ULTRA, PRO, BASIC]
STOCKS_ONBOARDING | [PREMIUM, ULTRA, PRO, BASIC]
MMF_ONBOARDING | [PREMIUM, ULTRA, PRO, BASIC]
STOCKS_UNLOCK | [PREMIUM, ULTRA, PRO, BASIC]
INVESTING | [PRO, ULTRA, PREMIUM]
UNLIMITED_POCKETS | [PRO, ULTRA, PREMIUM]
POCKET_CUSTOMIZATION | [PRO, ULTRA, PREMIUM]
FTW_WEEK_CHALLENGE | [PRO, ULTRA, PREMIUM]
RAINY_DAY | [PRO, ULTRA, PREMIUM]
GOALS | [PRO, ULTRA, PREMIUM] | Doesn't exist on Android
BRAIN | [PRO, ULTRA, PREMIUM]
CISA_ONBOARDING | [PRO, ULTRA, PREMIUM]
CASH_ISA_POCKET | [PRO, ULTRA, PREMIUM]
CISA_POCKET_CTA_GEN | [PRO, ULTRA, PREMIUM]
CARD_TILE | [ULTRA, PREMIUM]
ONE_P_CHALLENGE | [ULTRA, PREMIUM]
NAUGHTY_RULE | [ULTRA, PREMIUM]
SPEND_TRACKER | [ULTRA, PREMIUM]
STOCKS_BRACKET_1 | [PREMIUM]
LIVE_INTERCOM | [PREMIUM]
PENSIONS_BRACKET_1 | [PREMIUM] | iOS Only
FUNDS_BRACKET_1 | [PREMIUM]
RECURRING_ORDERS | [PREMIUM] | Android Only | This should be present on iOS also
STOCKS_RECURRING_ORDER | [PREMIUM] | Android Only | This should be present on iOS also
PRICE_ALERTS | [PREMIUM]
ETFS_BRACKET_1 | [PREMIUM] | EU Only
ETFS_BRACKET_2 | [PRO, PREMIUM] | EU Only
NOT_NEEDED | these are not live yet, they may be used in the future
MMF_RECURRING_ORDER | [PREMIUM]
CASH_ISA_RECURRING_ORDER | [PREMIUM]